## US List
Klipper
Story No. | User Stories | Description | Owner | Demo Date | Progress
1 | User Login | Show Login page Authentication Identify my role | Sanket | 2018-12-14 | Completed
2 | Attendance Report for last week | Show logged in User data (Any type of user) UI - No Filters Initially Show deficit data Highlight deficit data | Sanket |  | Completed
3 | Reportees - Attendance Report for last week | Visible for Lead/Admin Select reporting user Show selected user data | Krutika | 9th
4 | Attendance report for specified period | For Only Valid input Month From - to date Week | Sanket | 9th
5 | Reportees - Attendance report for specified period | For Lead/Admin only Month From - to date Week | Siddhesh | 9th
6 | Details of particular day | Click on UI element from table Popup on click Show all entry point data | Shweta | 10th
7 | Deployment | Identify Server for deployment Setup enviornment for deployment Come up with Deployment process | Sanket |  | In-Progress
8 | Show Total hrs for the selected data | Deficit hrs calculation according to policy document. Total Deficit Hrs, Total Overtime Hrs | Shweta
9 | Export options for Attendance Report | Export Report as csv,PDF | Sanket
10 | Supports working days | Show departmentwise working hrs calculations

## US 1
US 1 | User Login
Task No. | Tasks | Remaining Time | Assigned To | Status
1 | UI | - | sanket | Completed
2 | Authentication | - | sanket | Completed
3 | System should recognise Name,Role and ID | - | sanket | Completed
4 | Dummy password for users | - | Sidhdesh | Completed
5 | Klipper Logo on nav-bar | - | Krutika | Completed
6 | Remove Register button | - | Krutika | Completed

## US 2
US 2 | Attendance Report for last week
Task No. | Tasks | Remaining Time(hrs) | Assigned To | Status
1 | Show loggedin user data - API | 3 | Shweta | Completed
2 | Show loggedin user data - UI | - | Krutika | Completed
3 | Highlight deficiate data | 2 | Krutika | ToDo
4 | Integration | 2 | shweta | Completed

## US 3
US 3 | Reportees - Attendance Report for last week
Task No. | Tasks | Remaining Time | Assigned To | Status
1 | Visibilities of reportees : UI | 3 | Shweta | Completed
2 | List of reportees : API | 4 | Sidhdesh | completed
3 | Show selected user's data : API | 2 | Naushad | completed
4 | Show selected user's data : UI | 2 | Krutika | ToDo
5 | Integration | 3 | Krutika | ToDo
6 | Write test cases |  | Sidhdesh | ToDo

## US 4
US 4 | Attendance report for specified period
Task No. | Tasks | Remaining Time | Assigned To | Status
1 | Show user's data for selected date range: API | 2 | Sanket | Completed
2 | Show user's data for selected date range: UI | 2 | Sanket | Completed
3 | Get the data from Repository | 1 | Sanket | Completed
4 | Write test cases |  | Sidhdesh | ToDo

## US 5
US 5 | Reportees - Attendance report for specified period
Task No. | Tasks | Remaining Time | Assigned To | Status
1 | Show user's data for selected date range: UI | 2 | Sanket | To do
2 | Get the data from Repository | 1 | Sanket | To do
3 | Write test cases | 3 | Sidhdesh | To do

## US 6
US 6 | Details of particular day
Task No. | Tasks | Remaining Time | Assigned To | Status
1 | Display popup of detail access event on UI . | 6 | Shweta | Completed
2 | Design Popup for display access event . | 1 | Shweta | Completed
3 | Get list of detail of access event of a day. | 3 | Shweta | InProgress

## US9
US 9 | support for working days
Task No. | Tasks | Remaining Time | Assigned To | Status
1 | Show departmentwise working hrs calculations | - | sanket | Completed
2 | Map departmentwise working days | - | sanket | Completed
3 | Get working days info from Gourav |  | sanket | Completed
4 | Show data for non working days if punch available |  | shweta | Completed
5 | Include working hrs of non-working-days in total worked hrs. |  | shweta | Completed
6 | Exclude deficiate hrs of non-working-days |  | shweta | Completed
7 | Show non-working-days with hilighted color |  |  | InProgress
8 | Test cases |  |  | ToDo

## US 10
US 10 | Basic hrs regularization(for a day)
Task No. | Tasks | Remaining Time | Assigned To | Status
1 | only lead can regularize the time
2 | get regularization info from user: Service
3 | get regularization info from user: UI
4 | Test cases

## US 11
US 10 | Apply for a leave
Task No. | Tasks | Remaining Time | Assigned To | Status
1 | all users can apply for a leave | 3 hrs
2 | repository implementation | 1 day
3 | view applied leaves (for employee) | 1 day
4 | view applied leaves (for reportees) | 1 day
5 | Test cases | 1 day

## US 12
US 10 | Update leave
Task No. | Tasks | Remaining Time | Assigned To | Status
1 | employee can update un-realised leave | 1 day
2 | lead can update realised leave | 1 day
3 | Test cases | 1 day

## US 13
US 10 | Cancel leave
Task No. | Tasks | Remaining Time | Assigned To | Status
1 | employee can cancel un-realised leave | 1 day
2 | lead can cancel realised leave | 1 day
3 | Test cases | 1 day

## Issues
Issues
Task No. | Tasks | Remaining Time | Assigned To | Status | User story
1 | Case sensetive user name resolved | - | sanket | Completed | US1
2 | Login Messages updated | - | sanket | Completed | US1
3 | Message layout added at the bottom of the form | - | sanket | Completed | US1
4 | footer removed | - | sanket | Completed | US1
5 | KL logo addded on nav-bar | - | Krutika | Completed | US1